## User Stories
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create a task breakdown | 2024-03-16 | 2024-03-16
2 | Create a user story list | 2024-03-16 | 2024-03-16
3 | Create a design guide | 2024-03-16 | 2024-03-16
4 | Create high fidelity wireframes | 2024-03-17 | 2024-03-17
5 | Code initial version of the website (main page - header with a banner image and navigation, a footer) | 2024-03-20 | 2024-03-18
6 | Create development plans for the JavaScript libraries and widgets I plan to use | 2024-03-20 | 2024-03-19
7 | Submit Phase 1 | 2024-03-20 | 2024-03-19
8 | Code basic website structure | 2024-03-22 | 2024-03-22
9 | Implement API, graphics, map, links | 2024-03-24 | 2024-03-24
10 | Improve aesthetics using CSS | 2024-03-24 | 2024-03-24
11 | Conduct User Testing | 2024-03-27 | 2024-03-30
12 | Improve website page on user testing feedback | 2024-03-28 | 2024-03-30
13 | Gather user testing materials | 2024-04-01 | 2024-03-31
14 | Create 2-3 page design summary | 2024-04-01 | 2024-03-31
15 | Submit Phase 2 | 2024-04-01 | 2024-04-02
...